## SUMMARY
HRMS PROJECT IMPLEMENTATION TRACKER
SOFTWARE CLIENTS |  |  |  | MANAGED SERVICES CLIENTS
ACTIVE CLIENTS |  |  |  | ACTIVE CLIENTS
| Stand Alone | Centralized Portal | TOTAL |  | Stand Alone | Centralized / Payroll Portal | TOTAL
Live Clients | 3 | 1 | 4 | Live Clients | 23 | 6 | 29
Live with Pending Modules | 11 | 0 | 11 | Live with Pending Modules | 0 | 1 | 1
TOTAL | 14 | 1 | 15 | Payroll Clients | 11 | 31 | 42
|  |  |  | TOTAL | 34 | 38 | 72
ON GOING IMPLEMENTATION |  |  |  | ON GOING IMPLEMENTATION
| Stand Alone | Centralized Portal | TOTAL |  | Stand Alone | Centralized Portal | TOTAL
On going Implementation | 19 | 0 | 19 | On going Implementation | 4 | 1 | 5
Project Pipeline | 5 | 0 | 5 | Project Pipeline | 1 | 0 | 1
TOTAL | 24 | 0 | 24 | TOTAL | 5 | 1 | 6
YEAR TO DATE - SOFTWARE CLIENTS |  |  |  | YEAR TO DATE - MANAGED SERVICES
| Stand Alone | Centralized / Paryroll Portal | TOTAL |  | Stand Alone | Centralized / Paryroll Portal | TOTAL
TOTAL | 38 | 1 | 39 | TOTAL | 39 | 39 | 78
YEAR TO DATE - ALL CLIENTS
| Stand Alone | Centralized / Paryroll Portal | TOTAL
Active Clients | 37 | 38 | 75
Active with Pending Modules | 11 | 1 | 12
On Going Implementation | 23 | 1 | 24
Pipeline | 6 | 0 | 6
TOTAL | 77 | 40 | 117
INACTIVE CLIENTS |  |  |  | INACTIVE CLIENTS
| Stand Alone | Centralized / Paryroll Portal | TOTAL |  | Stand Alone | Centralized / Paryroll Portal | TOTAL
Terminated Projects | 17 | 2 | 19 | Terminated Projects | 0 | 0 | 0
TOTAL | 17 | 2 | 19 | TOTAL | 0 | 0 | 0

## Live Clients
Live Clients | [21 empty] | Versions
Full system requirement has been delivered and client has been using the software | [21 empty] | First version | V1
[22 empty] | Second Version | V2
[22 empty] | Latest Version | V3
Ref | Project ID | Client Name | Modules | Point of Contact | Client Type | Portal | Mobile App | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | Initial Data Receipt Date | Kick-off Meeting | Finalization of SOW | Date UAT Access Provided to Client | Date start of implementation | Date UAT Provided to Client | Go-live date | Implementation Duration (Days) | Mobile App Delivery | Sofware Version
1 | ND-EP-015 | ATS Travel | 1. Core HR 2. Payroll 3. Mobile Application |  | Managed Services | Stand Alone |  | Nick | Sajani | [10 empty] | 15 Sep 2023 | V3
2 | ND-EP-016 | Admiral Energy |  |  | Managed Services | Centralized Portal | [14 empty] | V3
3 | ND-EP-017 | AMAP | 1. Mobile App 2. Payroll 3. Time & Attendance 4. Visitor Management System |  | Managed Services | Stand Alone |  |  |  |  | 2021-08-09 | [9 empty] | V2
4 | ND-EP-018 | Beautiful Destinations |  |  | Managed Services | Stand Alone | [14 empty] | V3
5 | ND-EP-019 | Blanco | 1. Core HR 2. Payroll |  | Managed Services | Centralized Portal | [9 empty] | 2022-07-12 |  | 2023-02-20 |  |  | V3
6 | ND-EP-020 | Cambridge Medical Center |  |  | Managed Services | Stand Alone | [14 empty] | V2
7 | ND-EP-021 | Chanel | 1. Core HR 2. Payroll 3. Attendance & Timekeeping Module 4. Mobile Application | Marianne Estrada marianne.estrada@chanel.com | Managed Services | Stand Alone | [11 empty] | 2023-02-01 |  | 2023-05-26 | V3
8 | ND-EP-022 | DiaSorin |  |  | Managed Services | Stand Alone | [14 empty] | V3
9 | ND-EP-023 | Districo | 1. Core HR 2. Payroll |  | Managed Services | Stand Alone | [14 empty] | V3
10 | ND-EP-024 | Electric Way | 1. Core HR 2. Payroll 3. Mobile Application |  | Managed Services | Stand Alone |  |  |  | 2022-11-05 | [9 empty] | . | V3
11 | ND-EP-025 | Farfetch | 1. Core HR 2. Payroll |  | Managed Services | Stand Alone |  | Nick |  | 2023-01-11 | 2023-01-18 |  |  |  |  | 2023-01-16 |  | 2023-04-03 |  |  | V3
12 | ND-EP-026 | Ignite |  |  | Managed Services | Stand Alone |  |  |  |  | 2021-03-03 | [9 empty] | V3
13 | ND-EP-027 | IKEA | 1. Core HR 2. Payroll 3. Mobile Application |  | Managed Services | Stand Alone | [14 empty] | V3
14 | ND-EP-028 | Keystone Fellowship | 1. Core HR 2. Payroll 3. Mobile Application |  | Software Client | Centralized Portal |  | Nick | Sajani | 2022-11-18 | 2022-11-22 | [6 empty] | 2023-07-18 |  | 2023-06-30 | V3
15 | ND-EP-029 | MAF |  |  | Managed Services | Stand Alone | [14 empty] | V2
16 | ND-EP-030 | Med7 | 1. Core HR 2. Payroll 3. Mobile Application |  | Managed Services | Stand Alone |  |  |  |  | 2022-03-14 | [8 empty] | 2023-08-31 | V3
17 | ND-EP-031 | Medical Village |  |  | Managed Services | Stand Alone |  |  |  | 2022-11-05 | 2022-02-25 | [9 empty] | V3
18 | ND-EP-032 | Mena Moonshots | 1. Core HR 2. Payroll |  | Managed Services | Centralized Portal |  |  |  | 2022-11-05 | [10 empty] | V3
19 | ND-EP-033 | Mountain Air Shipping | 1. Core Core HR 2. Payroll 3. Task Management Module | HRBP: Maria Roselle Vindollo Sami Rai s.rai@maship.com | Managed Services | Centralized Portal |  | Nick | Jian | 2023-01-19 | 15-20-23 |  |  |  |  | 2023-03-03 |  | 2023-04-10 |  |  | V3
20 | ND-EP-034 | Neritum | 1. Core HR 2. Mobile Application |  | Managed Services | Stand Alone | [9 empty] | 2023-04-26 |  |  |  |  | V3
21 | ND-EP-035 | QMM |  |  | Managed Services | Stand Alone |  |  |  |  | 2021-09-26 | [9 empty] | V3
22 | ND-EP-036 | Roche Diagnostics | 1. Core HR 2. Payroll 3. Mobile Application |  | Managed Services | Stand Alone |  | Kawsar / Aman | Jian |  | 2022-12-14 |  |  |  |  | 2023-02-03 |  |  |  |  | V3
23 | ND-EP-037 | Sweetwater | 1. Core HR 2. Payroll 3. Reports |  | Managed Services | Centralized Portal | Yes |  |  |  | 2023-08-09 | [9 empty] | V3
24 | ND-EP-038 | Zendxb | 1. Core HR 2. Payroll 3. Attendance Management 4. Employee Self-Service 5. Mobile Application |  | Managed Services | Centralized Portal |  | Nick | Sajani |  | 2022-12-19 | [9 empty] | V3
25 | ND-EP-039 | J&T Express | 1. Core HR 2. Attendance & Shift Management 3. Asset Management Module 4. Mobile Application |  | Software Client | Stand Alone | Yes | Nick | Jian | [6 empty] | 2023-06-30 |  |  |  |  | V3
26 | ND-EP-040 | Seven Gym | 1. Core HR 2. Payroll 3. Attendance Management 4. Employee Self-Service 5. Mobile Application | Maria Kopylova maria@sevenofficial.com | Software Client | Stand Alone | Yes | Nick | Jian | [10 empty] | 2023-09-14 | V3
27 | ND-EP-041 | IHS |  |  | Managed Services | Stand Alone
28 | ND-EP-042 | Delonghi |  |  | Managed Services | Stand Alone
29 | ND-EP-043 | Roche Pharmaceuticals |  |  | Managed Services | Stand Alone
30 | ND-EP-044 | Arise |  |  | Managed Services | Stand Alone
31 | ND-EP-045 | Fendale |  |  | Managed Services | Stand Alone
32 | ND-EP-046 | NR Services |  |  | Managed Services | Stand Alone
33 | ND-EP-073 | Elevate DMC | 1. Core HR 2. Leave Management 3. Attendance Management 4. Payroll Management 5. Employee Self Service 6. Employee Asset Management 7. Task & Activity Management 8. Performance Management 9. Mobile Application 10. Reports |  | Software Client | Stand Alone | Yes | Arnold | Selphine | 2022-11-11 | 2022-11-28 | 2023-01-19 | 2022-12-13 | 2023-02-16 | 2023-02-16 | 2023-02-16 |  | 2023-06-01 | 170 | 2023-05-26
Formulas:
Implementation Duration (Days) = IF(Table1[[#This Row],[Kick-off Meeting]]=""," ",IF(Table1[[#This Row],[Go-live date]]>0,Table1[[#This Row],[Go-live date]]-Table1[[#This Row],[Kick-off Meeting]],TODAY()-Table1[[#This Row],[Kick-off Meeting]]))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on R40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No UAT System provided to the client.

## Payroll Clients
Payroll Clients
Clients who only availed the Payroll System
Ref | Project ID | Client Name | Client Type | Portal | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | User Data Receipt Date | Kick-off Meeting | Date UAT Access Provided to Client | Finalization of SOW | Date start of implementation | Go-live date | Implementation Duration (Days) | Mobile App Delivery | Sofware Version
1 |  | Schonfeld | Managed Services | Payroll Central
2 |  | ERES | Managed Services | Payroll Central
3 |  | IHS | Managed Services | Payroll Central
4 |  | Crown | Managed Services | Payroll Central
5 |  | Delonghi | Managed Services | Payroll Central
6 |  | AJC | Managed Services | Payroll Central
7 |  | FP Markets Ltd | Managed Services | Payroll Central
8 |  | KEYSIGHT TECHNOLOGIES | Managed Services | Payroll Central
9 |  | Innovaccer | Managed Services | Payroll Central
10 |  | Cross Point | Managed Services | Payroll Central
11 |  | Minerva Foods | Managed Services | Payroll Central
12 |  | QMM | Managed Services | Payroll Central
13 |  | Rémy Cointreau | Managed Services | Payroll Central
14 |  | Travix | Managed Services | Payroll Central
15 |  | YVOLV | Managed Services | Payroll Central
16 |  | Guggenheim | Managed Services | Payroll Central
17 |  | Hitachi | Managed Services | Payroll Central
18 |  | LMR Partners LLP | Managed Services | Payroll Central
19 |  | Spocto | Managed Services | Payroll Central
20 |  | MASSIVEMUSIC - FZCO | Managed Services | Payroll Central
21 |  | Dynamic Employment Services | Managed Services | Payroll Central
22 |  | TTONE GENERAL TRADING FZE | Managed Services | Payroll Central
23 |  | Oaktech Services FZ-LLC | Managed Services | Payroll Central
24 |  | Female Fusion | Managed Services | Payroll Central
25 |  | SOLED MANAGEMENT SERVICES | Managed Services | Payroll Central
26 |  | Hudson Bay Capital | Managed Services | Payroll Central
27 |  | AGILYSYS SOLUTIONS L.L.C FZ | Managed Services | Payroll Central
28 |  | MATRIX EXCHANGE LIMITED ADGM | Managed Services | Payroll Central
29 |  | Verition Management (DIFC) Limited - DIFC | Managed Services | Payroll Central
30 |  | Indee Enterprises L.L.C- FZ | Managed Services | Payroll Central
31 |  | MOOVE AFRICA | Managed Services | Payroll Central
32 |  | Wilhemsen | Managed Services | Stand Alone
33 |  | BIC World | Managed Services | Stand Alone
34 |  | Roche Pharmaceuticals | Managed Services | Stand Alone
35 |  | Nolus | Managed Services | Stand Alone
36 |  | Alfa Laval | Managed Services | Stand Alone
37 |  | Arise | Managed Services | Stand Alone
38 |  | Lincoln Holdings | Managed Services | Stand Alone
39 |  | Intersystems | Managed Services | Stand Alone
40 |  | Fendale | Managed Services | Stand Alone |  |  | 2022-11-05
41 | ND-EP-079 | Fayolle | Managed Services | Stand Alone | Jian | Selphine | 2023-10-02 | 2023-10-05 | 2023-11-07 | 2023-10-05 | 2023-10-05 | 2023-11-07 | 2023-11-07 | 2024-02-01 | 119
42 | ND-EP-082 | Survitec | Managed Services | Stand Alone | Sreekanth | Aless
Formulas:
Implementation Duration (Days) = IF(Table2[[#This Row],[Kick-off Meeting]]=""," ",IF(Table2[[#This Row],[Go-live date]]>0,Table2[[#This Row],[Go-live date]]-Table2[[#This Row],[Kick-off Meeting]],TODAY()-Table2[[#This Row],[Kick-off Meeting]]))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## On going Implementation
Ongoing Implementations
Active Implementations
Ref | Project ID | Client Name | Modules | Pending Modules | Point of Contact | Client Type | Portal | Mobile App | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | User Data Receipt Date | Kick-off Meeting | Date UAT Access Provided to Client | Finalization of SOW | Date start of implementation | Go-live date | Implementation Duration (Days) | Mobile App Delivery | Project Challenges | Remarks | Sofware Version
1 | ND-EP-062 | Adal AE | 1. Core HR 2. Payroll 3. Attendance Management 4. Employee Self-Service 5. Mobile Application | Phase 1: 1. User datasheet upload 2. Mobile Application | Rupali Upadhyay rupali@adal.ae | Managed Services | Stand Alone | Yes | Arnold | Aless | 2022-06-19 | 2022-09-13 |  |  |  |  | 2022-12-29 | [5 empty] | V3
2 | ND-EP-003 | Golf Kraft | 1. Core HR 2. Payroll 3. Attendance Management 4. Leave Management 5. Task & Project Management |  | Sanjay sanjay@golf-kraft.com | Software Client | Stand Alone | Yes | Benjamin | Lorrie | 2023-06-13 | 2024-01-09 | 2024-01-26 |  | 2024-02-15 |  | 2024-02-01 | [5 empty] | MCS
3 | #N/A | Legatum Group | 1. Payroll 2. Expense Claims 3. Loan Mgmt. 4. Reports |  | Name: Carla Viedge Email: Carla.Viedge@legatum.com Number: 0561132393 CC: evie.lelliott@legatum.com | Software Client | Stand Alone | Yes | Arnold | Lorrie | 2024-01-22 | 2024-01-24 | 2024-03-06 | [9 empty] | MCS
4 | ND-EP-085 | BinHendi Enterprises | 1. Core HR (Full) 2. Onboarding/Offboarding 3. Attendance 4. Task & Project Mgmt. 5. Payroll 6. Performance Mgmt. 7. Asset Mgmt. 8. ATS (Incl. Careers Page) 9. Reports 10. Mobile App |  | Sravani Nakkina s.nakkina@binhendi.com +971565458560 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2024-01-29 | 2024-02-05 |  | 2024-02-27 |  |  |  |  | 62 |  |  |  | MCS
5 | ND-EP-067 | GN Group | 1. Core HR 2. Payroll 3. Reports |  | Mohsen Elotafy motafey@gnhearing.com +971557562113 | Software Client | Stand Alone | Yes | Arnold | Lorrie | 2023-12-20 | 2023-12-22 | 2024-02-21 | 2024-02-26 |  |  | 2024-02-22 |  | 63 |  |  | MCS prod environment is in progress | MCS
6 | ND-EP-088 | Cybergate Defense | 1. Core HR (Full) 2. Attendance 3. Payroll 4. Reports 5. Mobile App 6. Performance Mgmt. 7. Task & Project Mgmt. 8. Offboarding 9. Emp Communication & Acknoledgement |  | Sweatha Subramanian sweatha@cybergate.tech +971526123179 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2024-01-31 | 2024-02-05 | [10 empty] | MCS
7 | ND-EP-002 | Club Lab Golf | 1. Core HR 2. Payroll 3. Reports 4. Task & Project Mgmt. |  | Reg Van Rooyen reg@clublabgolf.com | Software Client | Stand Alone | Yes | Benjamin | Lorrie | 2023-06-05 | [10 empty] | The client organization is going through some changes, the HRMS project discussion will again pick up by mid of next year. | MCS
8 | ND-EP-081 | British Oak Montessori | 1. Core HR |  | Varsha Ramnani HRBP | Managed Services | Centralized Portal | No | Arnold | Lorrie | 2023-12-26 | 2024-02-23 | 2024-02-23 | 2024-02-08 |  |  |  |  | 81 |  |  | MCS prod environment is in progress | MCS
9 | ND-EP-051 | Systra Egypt | 1. Core HR 2. Attendance Management 3. Leave Management 4. Payroll Management 5. PRO Module 6. Employee Self-Service 7. Mobile Application 8. Reports | Phase 1: 1. Core HR 2. Employee Self-Service 3. Attendance Management 4. Leave Management 5. Payroll Management (Standard) Phase 2: 6. PRO Module 7. Mobile Application 8. Reports | Sidi Ziane smziane@systra.com Ayman Elkhouly aelkhouly@systra.com | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-02-28 | 2023-03-06 | 2023-03-08 | 2023-03-06 | 2023-10-10 |  |  |  | 420 |  |  |  | V3
10 | ND-EP-052 | Systra KSA | 1. Core HR 2. Attendance Management 3. Leave Management 4. Payroll Management 5. PRO Module 6. Employee Self-Service 7. Mobile Application 8. Reports | Phase 1: 1. Core HR 2. Employee Self-Service 3. Attendance Management 4. Leave Management 5. Payroll Management (Standard) Phase 2: 6. PRO Module 7. Mobile Application 8. Reports | Osama AlRashed oalrashed@systra.com Ayman Elkhouly aelkhouly@systra.com | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-02-26 | 2023-03-06 | 2023-03-08 | 2023-03-06 | 2023-10-14 |  |  |  | 420 |  |  |  | V3
11 | ND-EP-069 | Dentsu | 1. Payroll 2. Workday Integration |  | Kaitlin Kwiatkowski Kaitlin.Kwiatkowski@dentsu.com | Managed Services | Stand Alone | No | Sreekanth | Jian |  |  |  | 2023-05-30 | 2024-01-25 |  |  |  | 335 |  |  | Client UAT Testing | V3
12 | ND-EP-048 | Eathos | 1. Core HR 2. Leave Management 3. Attendance Management 4. Payroll Management 5. Employee Self Service 6. PRO Module 7. Performance Management Module 8. Asset Management Module 9. Task Management Module 10. ATS Module 11. Mobile App 12. Support Module | Phase 2: 1. Core HR 2. Leave Management 3. Attendance Management 4. Employee Self Service Phase 3: 5. PRO Module 6. Performance Management Module 7. Asset Management Module 8. Task Management Module 9. ATS Module 10. Mobile App 11. Support Module | Midhun Hubert mhubert@eathos.net +971 4 317 3200 EXT 218 Muhannad Alshehri - KSA malshehri@eathos.net + 966 59 240 90 16 | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-07-28 | 2023-07-31 | 2023-08-16 | 2023-08-21 | 2023-10-17 | 2023-09-18 | 2023-09-18 |  | 252 | 2024-01-19 |  |  | V3
13 | ND-EP-056 | Soho | 1. Performance Management 2. Employee Self Service 3. Asset Management 4. Payroll Management 5. Onboarding & Offboarding 6. Reports 7. Budgeting 8. Mobile Application 9. ATS Module | Phase 1: 1. Employee Self Service 2. Payroll Management Phase 2: 1. Performance Management 2. Asset Management 3. Onboarding & Offboarding 4. Reports 5. Budgeting 6. Mobile Application 7. ATS Module | Ziad Moghrabi z.moghrabi@sohome.ae Sondos Elkollaly s.elkollaly@sohome.ae | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-24 | 2023-12-12 |  |  |  | 157 | 2024-01-19 |  |  | V3
14 | ND-EP-059 | Alfa Laval | 1. Time & Attendance Management 2. Core HR 3. Offboarding 4. Mobile Application | 1. Time & Attendance Management 2. Core HR 3. Offboarding 4. Mobile Application | Rohan Pawar rohan.pawar@alfalaval.con +918799969051 | Managed Services | Stand Alone | No | Arnold | Lorrie | 2023-11-29 | 2023-12-01 | 2024-03-11 | 2023-12-13 |  |  |  |  | 138 |  |  |  | V2 (Basil to check)
15 | ND-EP-057 | OQ Trading | 1. Core HR 2. Payroll 3. Performance Management 4. Attendance & Shift Management 5. Asset Management 6. Mobile Application | Phase 1: 1. Core HR 2. Payroll 3. Attendance & Shift Management Phase 2: 1. Performance Management 2. Asset Management 3. Mobile Application | Shannon Naude shannon.naude@oq.com +971566809758 Rodney Mugwendere rodney.mugwendere@oq.com +971501074193 | Software Client | Stand Alone | Yes | Arnold | JIan | 2023-05-23 | 2023-06-15 | 2023-11-23 | 2023-12-19 | 2024-02-01 |  |  |  | 132 |  |  |  | V3
16 | #N/A | Home Apparel | 1. Core HR 2. Payroll |  | Job Brian jobbrian@homeapparel254.com +254707706005 Karen Bururia karenbururia@homeapparel254.com +254786413934 | Software Client | Stand Alone | Yes | Sherul | Jian | 2023-09-27 | 2023-12-11 | 2023-12-19 | 2023-12-21 | 2024-01-12 | 2024-01-22 | 2024-01-22 |  | 130 |  |  |  | V3
17 | ND-EP-064 | ILF Consulting | 1. Payroll Central |  | Mahmoud Fawzi +971 / 56 503 4671 mahmoud.fawzi@ilf.com | Software Client | Stand Alone | No | Arnold | Aless | 2023-12-05 | 2023-12-05 | 2024-02-24 | 2023-12-26 | 2024-03-01 |  |  |  | 125 |  |  |  | MCS
18 | ND-EP-058 | Babilou Education | 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Payroll Management 5. Leave Management 6. Employee Engagement 7. Performance Management 8. Task & Project Management 9. Asset Management 10. Employee Transitions 11. Training Management 12. BI Reporting & Analytics 13. Mobile Application 14. API Integration | Phase 1: 1. Payroll Phase 2: 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Leave Management 5. ATS Phase 3: 1. Employee Engagement 2. Performance Management 3. Task & Project Management 4. Asset Management 5. Employee Transitions 6. Training Management 7. BI Reporting & Analytics 8. Mobile Application 9. API Integration | Navya Kumar navya.kumar@babiloueducation.com +971 55 263 8179 | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-12-06 | 2023-12-07 | 2023-12-12 | 2024-01-05 | 2024-01-12 |  |  |  | 115 |  |  |  | V3
19 | #N/A | Fatorah | 1. Accounting 2. Core HR | 1. HRMS | Indhu Nithin indhu.nithin@fatorah.ae | Software Client | Stand Alone | Yes | Sherul | Jian | 2023-11-29 | 2023-12-07 | 2024-01-12 | 2024-01-23 | 2024-02-13 |  |  |  | 97 |  |  | Client is shifiting offices hence the delay in responses | MCS
20 | ND-EP-065 | Dnata Logistics | 1. Core HR 2. Payroll 3. Onboarding/Offboarding 4. Performance Management 5. Task Management 6. Attandance & Shift Management |  | Amruta Nair amrutha.nair@dnatalogistics.com +971 55 185 0914 | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-11-29 | 2023-12-11 | 2024-01-05 | 2024-01-30 |  |  |  |  | 90 |  |  |  | MCS (Convert)
21 | ND-EP-012 | Project Pulse | 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Payroll Management 5. Leave Management 6. Onboarding & Offboarding 7. Performance Management 8. Mobile Application |  | Salma Elmasry pa@projectpulse.ae Adnan Wadha adnanw@projectpulse.ae | Software Client | Stand Alone |  | Sherul | Lorrie | 2023-05-19 |  |  | 2024-02-01 |  |  |  |  | 88 |  |  | Client currently facing tech issues | MCS
22 | ND-EP-063 | API LLC | 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Payroll Management 5. Leave Management 6. Onboarding & Offboarding 7. Performance Management 8. Task & Project Management 9. Asset Management 10. Mobile Application |  | Naeem Pate npatel@apidubai.ae 0567111773 | Software Client | Stand Alone | Yes | Arnold | Jian | 2024-01-29 | 2024-01-31 | 2024-01-25 | 2024-02-13 |  |  |  |  | 76 |  |  | Cancelled Face to Face Scoping - to to be rescheduled for the following week | MCS
23 | #N/A | Santechture | 1. Accounting 2. HRMS |  | Rohilla Fernandes rfernandes@santechture.com | Software Client | Stand Alone | Yes | Sherul | Jian | 2023-12-11 | 2023-12-13 | 2024-01-25 | 2024-02-20 | 2024-02-16 |  |  |  | 69 |  |  | Client is shifiting offices hence the delay in responses | MCS
24 | ND-EP-087 | Abu Dhabi Advanced Motors | 1. Core HR (Full) 2. Attendance 3. Payroll 4. Reports 5. Mobile App |  | HRBP: Varsha Ramnani Name: Angel Wesley Email: Angel.Wesley@cyvnholdings.com Name: Bernd Erich Schwendtke Email: Bernd.Schwendtke@cyvnholdings.com Number: 058 877 4884 CC: Sara Badwan Sara.Badwan@cyvnholdings.com | Managed Services | Stand Alone | Yes | Arnold | Selphine | 2024-01-26 | 2024-01-31 |  | 2024-02-21 |  |  |  |  | 68 |  |  | Need to inform Cali when performance management is being implemented so that she can collect payment. | MCS
Formulas:
Implementation Duration (Days) = IF(Table3[[#This Row],[Kick-off Meeting]]=""," ",IF(Table3[[#This Row],[Go-live date]]>0,Table3[[#This Row],[Go-live date]]-Table3[[#This Row],[Kick-off Meeting]],TODAY()-Table3[[#This Row],[Kick-off Meeting]]))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on N9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on O9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No UAT System provided to the client.
Note on Q9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No standard SOW document prepared.
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Nov 22, 2023
Note on K18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Nov 22, 2023
Note on K20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Nov 22, 2023
Note on U20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attendance only
Note on U21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attendance only
Note on O25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1st week of Jan
Note on O27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Tentative: 18 Dec Reply: Initial documents have not been shared as of today
Note on O28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1st week of Jan
Note on L30: Jian Clarice P. Mercado: • Original contract signed on 11/12/2023 • Addendum signed on 29/01/2024
Note on O31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1st week of Jan

## Live with Pending Modules
Live with Pending Modules
Client has been using the system but there are still pending modules to be implemented
Ref | Project ID | Client Name | Modules | Pending Modules | Point of Contact | Client Type | Portal | Mobile App | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | User Data Receipt Date | Kick-off Meeting | Finalization of SOW | Date start of implementation | Date UAT Provided to Client | Go-live date | Implementation Duration (Days) | Mobile App Delivery | Project Challenges | Remarks | Sofware Version
1 | ND-EP-070 | Al Emad Cars | 1. Core HR 2. Payroll 3. Attendance Management 4. Employee Self-Service 5. Performance Management | 1. Performance Management (Client Testing) | Muhammad Azeen Ahsan azeem@quicklease.ae +971504931747 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2023-01-03 | 2023-01-10 | 2023-01-30 | 2023-02-06 | 2023-03-30 | 2023-03-30 | 2023-05-19 | 2023-09-27 | #VALUE! | 2023-08-31 |  |  | V3
2 | ND-EP-071 | Ayana Holding (VX Studio) | 1. Core HR 2. Performance Management 3. Mobile Application 4. Task & Project Management 5. Attendance 6. Asset Management 7. Reports | 1. Onboarding / Offboarding (testing) |  | Software Client | Stand Alone | Yes | Arnold | Selphine | 2023-03-31 | 2023-04-27 | 2023-04-27 | 2023-04-11 | 2023-05-03 | 2023-05-03 | 2023-05-17 | 2023-06-19 |  | 2023-07-25 |  |  | V3
3 | ND-EP-072 | EDF | 1. Core HR 2. Payroll 3. Onboarding & Offboarding 4. Support Modules 5. Mobile Application | 1. Air ticket functionality (payroll) | Nora Himri nora.himri@edf.com +971503439096 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2023-05-26 | 2023-06-08 | 2023-06-08 | 2023-06-08 | 2023-08-11 | 2023-08-11 | 2023-08-21 | 2023-11-16 |  | 2024-01-30 |  |  | V3
4 | ND-EP-075 | Nasco - Internal | 1. Core HR 2. Payroll 3. PRO module 4. Performance Management Module 5. Employee Self-Service 6. Attendance Module 7. HR Reports 8. Admin Access 9. Employee Directory 10. Resources 11. Mobile Application | 1. Performance Management (Client Testing) | Jacob Mundakal jacob.mundakal@nascodubai.com +971507492007 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2022-08-31 | 2022-09-05 | 2022-09-13 | 2022-09-22 |  | 2022-09-29 |  | 2023-06-02 |  | 2023-06-30 |  |  | V3
5 | ND-EP-076 | R Mixed | 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Payroll 5. Leave Management 6. Onboarding & Offboarding 7. Performance Management 8. Task & Project Management 9. Asset Management 10. Support | 1. Payroll - For Client Testing 2. Onboarding & Offboarding 3. Performance Management 4. Asset Management - For Client Testing | Stephanie Al Feghali stephanie.feghali@rmixed.com +971569982061 Riwa Hanna riwa.hanna@rmixed.com +971509671216 | Software Client | Stand Alone | Yes | Arnold | Selphine | 2023-07-11 | 2023-07-14 | 2023-07-20 | 2023-07-26 | 2023-08-14 | 2023-08-14 | 2023-08-25 | 2023-10-25 | 62 | 2024-01-04 | Client is taking time to test all the pending modules. Not responding to email follow-ups related to Onboarding/Offboarding and Assets |  | V3
6 | ND-EP-078 | Safran | 1. Core HR 2. Leave Management 3. Attendance Management 4. Payroll 5. PRO Module 6. Performance Management 7. Asset Management 8. Task Management 9. ATS Module | 1. Asset Management 2. Performance Management - Client Testing 3. ATS Module | Sara BAROUD sara.baroud@safrangroup.com 050 722 6716 Steeve ZEHENNI steeve.zehenni@safrangroup.com 058 528 6280 | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-06-09 | 2023-06-15 | 2023-06-16 | 2023-06-15 | 2023-09-11 | 2023-08-24 | 2023-09-11 | 2023-12-08 | 63 | 2024-01-04 |  |  | V3
7 | #N/A | Dumany | 1. Core HR 2. Payroll 3. Onboarding & Offboarding 4. Asset Management 5. Mobile App | 1. Onboarding, Offboarding,Visa - QA Testing 2. Asset Management |  | Software Client | Stand Alone | Yes | Gee | Jian | 2023-09-27 | 2023-11-16 | 2023-11-27 | 2023-11-16 | 2023-12-18 |  |  | 2024-01-25 |  | 2024-03-04 |  |  | V3
8 | ND-EP-061 | Socar Logistics | 1. Core HR 2. Employee & Admin Self Service 3. Onboarding & Offboarding 4. Payroll Management 5. Attendance Management 6. Shift Management 7. Reports 8. Document Expiry Tracking 9. Built-in Notifications 10. Employee Directory 11. Social World | Phase 2: 1. Letters Module 2. Payroll Management 3. Attendance Management 4. Shift Management 5. Onboarding & Offboarding 6. Reports 7. Document Expiry Tracking 8. Built-in Notifications | Ekaterina Khaitova ekhaitova@socarlogistics.com | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-11-03 | 2023-12-11 | 2024-01-22 | 2024-01-10 | 2024-01-26 | 2024-01-10 | 2024-01-10 | 2024-03-01 |  |  |  | As per Ekaterina, Phase 2 implementation will be put on hold as they want first to test the Phase 1 modules on how employees will react to it. Phase 2 will resume by end of March 2024. | V3
9 | ND-EP-054 | Systra UAE | 1. Core HR 2. Attendance Management 3. Leave Management 4. Payroll Management 5. PRO Module 6. Employee Self-Service 7. Mobile Application 8. Reports | Phase 1: 1. Payroll Management (Standard) Phase 2: 2. PRO Module 3. Mobile Application 4. Reports | Augustin Larroque alarroque@systra.com Katrina Dampil kdampil@systra.com Ayman Elkhouly aelkhouly@systra.com | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-02-28 | 2023-03-06 | 2023-03-08 | 2023-03-06 | 2023-09-04 | - | - | 2024-03-01 | 81 | 2024-01-29 |  |  | V3
10 | ND-EP-055 | Party Social | 1. Core HR 2. Payroll 3. Performance Management 4. Task & Project Management 5. Attendance & Shift Management 6. Accounting System integration with Quickbooks 7. Support Modules 8. Mobile Application | Phase 2: 6. Performance Management 7. Accounting System integration with Quickbooks | Asma El Naili asma.elnaili@modernhr.org Iman El Huni iman@partysocial.ae | Software Client | Stand Alone | Yes | Arnold | Aless | 2023-06-06 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-12-19 |  |  | 2024-03-14 | 420 | 2024-01-19 |  |  | V3
11 | ND-EP-047 | DIFC Courts | 1. Core HR 2. Attendance Management 3. Leave Management 4. Payroll Management 5. PRO Module 6. Asset Management 7. Employee Self Service (ESS) 8. Performance Management 9. Recruiting & ATS (if required) 10. Onboarding & Offboarding 11. Training Module | Phase 2: 1. Attendance Management 2. PRO Module 3. Asset Management 4. Performance Management 5. Recruiting & ATS (if required) 6. Onboarding & Offboarding 7. Training Module | Adil Khan adil.khan@difccourts.ae +971 56 460 6557 Arul Jose Vigin arul.vigin@difccourts.ae +971 50 899 0501 | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-09-26 | 2023-10-04 | 2023-10-21 | 2023-11-16 | 2024-01-03 | 2024-01-04 | 2024-11-13 | 2024-03-19 | 420 |  |  |  | V3
12 | ND-EP-083 | Cinepolis Gulf Entertainment | 1. Payroll 2. Leave Management | 1. Leave Management | Akshay Dasgupta HRBP | Managed Services | Payroll Central | No | Arnold | Aless | 2023-12-15 | 2024-01-08 | 2024-01-08 | 2024-01-18 | 2024-01-19 | 2024-01-19 | 2024-02-01 | 2024-02-01 | 335 | N/A
Formulas:
Implementation Duration (Days) = IF(Table3[[#This Row],[Kick-off Meeting]]=""," ",IF(Table3[[#This Row],[Go-live date]]>0,Table3[[#This Row],[Go-live date]]-Table3[[#This Row],[Kick-off Meeting]],TODAY()-Table3[[#This Row],[Kick-off Meeting]]))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on K9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cant find this module on Jira board, @Jian Clarice P. Mercado please assist here
Note on K10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on E11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ahmed is fixing issues raised from QA, also working on user manual. Planning to complete by Wednesday
Note on K11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on P11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on R11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No UAT System provided to the client.
Note on E12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No comment from client on the modules they are testing, I am still following up with Vian on Performance management.
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on N15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: User data sheet shared on 22/01/2024.
Note on K16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Nov 22, 2023
Note on K17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Nov 22, 2023
Note on O17: Jian Clarice P. Mercado: Reignition from Asma - Nov 2023
Note on U17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Attendance only

## Projects On-Hold
Projects On-Hold
Client has no response
Ref | Project ID | Client Name | Modules | Pending Modules | Point of Contact | Client Type | Portal | Mobile App | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | User Data Receipt Date | Kick-off Meeting | Finalization of SOW | Date start of implementation | Date UAT Provided to Client | Go-live date | Implementation Duration (Days) | Mobile App Delivery | Project Challenges | Remarks | Sofware Version
1 | #VALUE! | Mumzworld | 1. Core HR 2. Payroll 3. Employee Onboarding and Offboarding Module 4. Performance Management Module 5. Task & Project Management Module 6. ATS Module 7. Mobile Application 8. Support Module | 1. Payroll 2. Performance Management 3. Mobile Application | HRBP: Soma Raj Gail Maeko gail@mumzworld.com | Managed Services | Stand Alone | Yes | Arnold | Lorrie | 2022-06-26 | 2022-06-07 | 2022-06-23 | 2022-06-27 | 2023-04-04 | 2022-06-20 | 2022-08-19 | 2022-09-28 | #VALUE! | #VALUE! |  |  | V3
2 | ND-EP-062 | Systra Turkey | 1. Core HR 2. Attendance Management 3. Leave Management 4. Payroll Management 5. PRO Module 6. Employee Self-Service 7. Mobile Application 8. Reports |  | Ozge Altug oaltug@systra.com Ayman Elkhouly aelkhouly@systra.com | Software Client | Stand Alone | Yes | Arnold | Aless | 1 Mar 2023 | 6 Mar 2023 | 8 Mar 2023 | 6 Mar 2023 | 14 Oct 2023 |  | 14 Oct 2023 |  |  |  |  | Project on hold as per client.
3 | ND-EP-003 | Shop Valyou | 1. Core HR 2. Payroll |  |  | Software Client | Stand Alone | Sherul
4 | #N/A | Saverglass | 1. Core HR 2. Payroll 3. Performance Management Module 4. Attendance & Timekeeping Module 5. ATS Module 6. Task Management Module 7. Onboarding & Offboarding Module 8. Asset Management Module 9. Mobile Application 10. Training & Development 11. Budgeting & Analytics 12. SAP Integration | Phase 2: 1. Performance Management Module 2. ATS Module 3. Onboarding & Offboarding Module Phase 3: 4. Training & Development 5. Budgeting & Analytics 6. SAP Integration | Deepa Shetty uds@saverglass.ae +971-56-509-4108 Satya uny@saverglass.ae +971 56 118 2214 | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-01-17 | 2023-01-31 | 2023-02-02 | 2023-02-06 | 2023-06-06 | 2023-05-08 | 2023-05-08 |  |  | 2023-09-05
5 | ND-EP-085 | RAS Investment Group | 1. Core HR 2. Attendance Management 3. Employee Self Service 4. Payroll 5. Leave Management 6. Onboarding & Offboarding 7. Task & Project Management 8. Asset Management 9. Support | 1. Onboarding & Offboarding 2. Asset Management | Mohamad Zarka Yuzana Khin hr@rasig.ae +971558056957 | Software Client | Stand Alone | Yes | Arnold | Jian | 2023-08-14 | 2023-08-23 | 2023-09-05 | 2023-09-12 | 2023-11-01 | 2023-10-09 | 2023-10-10 |  | 1900-03-02 | 1900-03-02 | Client is not responding despite several emails from the Implementation Team and Cali. |  | V3
Formulas:
Implementation Duration (Days) = IF(Table3[[#This Row],[Kick-off Meeting]]=""," ",IF(Table3[[#This Row],[Go-live date]]>0,Table3[[#This Row],[Go-live date]]-Table3[[#This Row],[Kick-off Meeting]],TODAY()-Table3[[#This Row],[Kick-off Meeting]]))
Mobile App Delivery = IF(Table3[[#This Row],[Kick-off Meeting]]=""," ",IF(Table3[[#This Row],[Go-live date]]>0,Table3[[#This Row],[Go-live date]]-Table3[[#This Row],[Kick-off Meeting]],TODAY()-Table3[[#This Row],[Kick-off Meeting]]))
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on M8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on N8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on O8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on Q8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.

## Project Pipeline
Project Pipeline
System build has not started yet
Ref | Project ID | Client Name | Modules | Point of Contact | Client Type | Portal | Project Manager | Project Coordinator | Contract Sign Date | Data Gathered Start Date | User Data Receipt Date | Kick-off Meeting | Finalization of SOW | UAT Access | Remarks
1 | ND-EP-086 | TMF Group | 1. Payroll Central |  | Software Client | Stand Alone | Arnold | Jian | 2024-03-01 | [5 empty] | Contract under negotiation
2 | ND-EP-001 | EMLTC | 1. Core HR 2. Payroll |  | Software Client | Stand Alone | Sherul | Aless
3 | #N/A | Majid Al Futtaim | 1. Shift Management 2. Workforce Planning |  | Software Client | Stand Alone | [8 empty] | Procurement process still underway.
4 | #N/A | Hitachi | 1. Leave Management |  | Managed Services | Stand Alone | Arnold | Aless | [6 empty] | Client to decide how to proceed, either full leave management or just balance tracking.
5 | #N/A | Nasco Oman | 1. HR Module (Employee/Manager Self Service) 2. PRO Module 3. Performance Management Module 4. Attendance Module 5. Reports 6. Mobile Application |  | Software Client | Stand Alone | Arnold | Selphine | 2024-03-05 |  |  | 2024-03-18
6 | ND-EP-079 | Fayolle | 1. Core HR 2. Onboarding & Offboarding 3. Attendance Management 4. Mobile Application (UAE, France, Ivory Coast, Cameroon) |  | Software Client | Stand Alone | Arnold | Jian | 2024-03-18
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Terminated Projects
Terminated Clients
Clients who terminated their contract
Ref | client_name | modules | client_type | portal | project_manager | project_coordinator | contract_sign_date | Data Gathered Start Date | user_data_receipt_date | kick_off_meeting | finalization_of_SOW | date_start_of_implementation | go_live_date | date_of_email_cancelation | termination_date | reason_for_termination
1 | ADQ |  | Managed Services | Stand Alone
2 | Al Handal |  | Managed Services | Centralized Portal
3 | Al Jalal Trading |  | Managed Services | Stand Alone
4 | Amzone |  | Managed Services | Stand Alone
5 | Asfar |  | Software Client | Stand Alone
6 | BW Pavilion |  | Managed Services | Stand Alone
7 | DOCIB Group |  | Managed Services | Stand Alone
8 | German Pavilion |  | Managed Services | Stand Alone
9 | ITFAQ |  | Software Client | Centralized Portal | Nick | Jian | [8 empty] | 2023-11-01
10 | Marina Pharm |  | Managed Services | Stand Alone
11 | Omnipresent |  | Managed Services | Stand Alone
12 | Signworks |  | Managed Services | Stand Alone | [9 empty] | 2023-11-07
13 | The Aimes |  | Software Client | Stand Alone | Nick | Sajani | [8 empty] | 2023-09-22
14 | The Grooming Company |  | Software Client | Stand Alone
15 | TIEBLE |  | Managed Services | Stand Alone
16 | Udrive |  | Managed Services | Stand Alone
17 | Ele Interiors - Secret Garden | 1. CoreHR 2. Leave 3. Attendance 4. Payroll 5. Self Service | Software Client | Stand Alone | Nick | Jian | 2023-05-03 | 2023-06-05 |  |  |  |  | 2023-07-31 | 2023-11-21 |  | Not confident about the outcome moving forward and wasting any more time
18 | Dubai Autism Center | 1. Core HR 2. Payroll 3. Performance Management Module 4. PRO / Onboarding Module 5. Support Modules 6. Mobile Application | Software Client | Stand Alone |  |  | 2022-10-05 | 2023-01-30 | 2023-02-17 | 2023-01-30 |  |  | 2023-03-14 | 2024-01-09 | 2024-01-09 | Tue 09/01/2024 12:20 PM: Decided not to renew the agreement
19 | Sanctuary | 1. Core HR 2. Payroll 3. Employee Onboarding Module 4. Task and Project Management Module 5. Admin Access 6. Standardized Reports 7. Employee Directory 8. Resources 9. Mobile Application 10. Performance Management | Managed Services | Stand Alone | Arnold | Selphine | 2022-07-14 | 2022-08-02 | 2022-08-30 | 2022-08-11 | - | - | 2023-01-04 | 2024-02-19 | 2024-02-19 | Decided not to renew the agreement
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Cali, waiting for the confirmation of client whether they will renew or cancel.
Note on L25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No UAT System provided to the client.
Note on M25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old process. No standard SOW document prepared.
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Per Cali, waiting for the confirmation of client whether they will renew or cancel.
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Effective Jan 22, 2024
Note on L26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.
Note on M26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Old client. No access to Stephanie's mailbox.